## 141216
Date | 2016-12-14
Time | 1:30pm
Discussion | Views and testing of the work done till date
Short Term Milestone (within a week) | Under the Procurement Module, Colour Palette for the Theme, Automatically add new manufacturer name from the list as selected; PO not to save without a PO Number
Mid Term Milestone | Report Icon on the Side Bar
Long Term Milestone | Geoscape Logo for cursor- graduated small to large gold balls; Reporting Parameters on Report Engine; Static Side Bar; The Services Module
Immediate Requirements
Next Proposed Meeting | 2016-12-15
Requirements for Next Proposed Meeting
Expected End- date | FYE 2017
Next Payment Due | N/A

## 151216
Date | 2016-12-15
Time | 9:00am | Status
Discussion | Testing of the work done till date by Process Owners
Short Term Milestone (within a week) | 1) Add Excel Uploader to the RFQ Builder module to enable user import multi-item RFQ into the system | Done
| 2) Creation Date of RFQs should be from present to 2 weeks back in time. If more than two weeks, approval from LM should be sought | Done
| 3) Notes on the Line Items Form for RFQ Builder module | Done
| 4) Confirm reason for failure on creating new RFQs (bug) | Done
| 5) UOM (Unit of Order Measurement) to be upgraded to include more terms commonly used by the Procurement Team | Done
| 6) To Rebuild RFQ/Quotation Template on the Reporting Server (Quotation printer) | Done
| 7) Create various Reporting Criteria (Build more logics) | Pending: This would depend on the criterion that would be used for searches
| 8) Add Partially Submitted Status to RFQs | In progress
| 9) Create Color Codes for Statuses on RFQs | Done
| 10) POs should contain other costs like Freight, Customs etc (Should be tick boxes with text boxes for input) | Done
| 11) Put all currencies to enable changing of currencies on the fly | Done
Mid Term Milestone | Report Icon on the Side Bar | Pending
Long Term Milestone | Geoscape Logo for cursor- graduated small to large gold balls; Reporting Parameters on Report Engine; Static Side Bar; The Services Module | Pending
Immediate Requirements
Next Proposed Meeting | 2016-12-22
Requirements for Next Proposed Meeting
Expected End- date | FYE 2017
Next Payment Due | N/A

## 130117
Date | 2017-01-12
Time | 1:00pm
Discussion | Testing to see if the identified bugs have been resolved. | Status
Short Term Milestone (within a week) | 1) Add Remark to PO Cost Tracker on the PO Creation Form | Done
| 2) Include Discounts on the Cost Tracker on PO Creation Form | Done
3) Create Installmental Payment Tracker on the PO Creation Form
| 4) Enter Details of Manufacturer on the Dynamic Manufacturer Creation Form | Done
5) Show Appropriate Cost on Each PO (Emphasis on Split POs)
6) To Rebuild RFQ/Quotation Template on the Reporting Server (Quotation printer) - carried over from last time
7) Create various Reporting Criteria (Build more logics)
| 8) Create Color Codes for Statuses on RFQs - Untested | Done
| 9) Change the Sidebar to GOLD and other text Black (Geoscape Colors) | Done
10) Create more colourful Reporting Templates (Team-Furmanite sample used)
Mid Term Milestone | Report Icon on the Side Bar
Long Term Milestone | Geoscape Logo for cursor- graduated small to large gold balls; Reporting Parameters on Report Engine; Static Side Bar; The Services Module
Immediate Requirements
Next Proposed Meeting | 2017-01-19
Requirements for Next Proposed Meeting
Expected End- date | FYE 2017
Next Payment Due | N/A